## Sheet1
id | project_name | client_name | software | vendor | start_date | deadline | status | description | file_path | user_id
9 | Central Cuisine Restaurants & Events Center (Fire N Ice) | Central Cuisine Restaurants & Events Center (Fire N Ice) | ODOO | ODOO SA | 2025-07-09 | 2025-07-31 | Started | Product: Odoo Pos Implementation Owner: Jayshil Action Items: UAT – WIP, due (15/07/2025). Progress: 30% Total Billing: $13,216.75 Total Billed: $7,758 |  | 1
8 | Cricket Fiji | Cricket Fiji | MYOB | MYOB Australia | 2025-07-09 | 2025-07-31 | Started | Product: MYOB Implementation Owner: Jayshil Action Items: Customer to get back on implementation. Project is fully paid. Issues: CUSTOMER DELAY Progress: 5% Total Billing: $4,947 Total Billed: $4,947 |  | 1
7 | MY Transport | MY Transport | MYOB | MYOB Australia | 2025-07-09 | 2025-07-31 | In Progress | Product: MYOB Implementation Owner: Jayshil Action Items: Forms customization – form 1 completed. Waiting for the second login to customize the final form. (awaiting customer) Check On Sign-Off Progress: 70% Total Billing: $9,112 Total Billed: $9,112 |  | 1
6 | LTA | LTA | LTA Report | Custom Development | 2025-07-09 | 2025-07-15 | In Progress | Product: LTA Report Owner: Jayshil Action Items: Get AP Sign off XL Connect report development – WIP Configure payroll journal -WIP. |  | 1
5 | Douglas Salvage and Towage (Solomon Islands) | Douglas Salvage and Towage (Solomon Islands) | MYOB | MYOB Australia | 2025-07-09 | 2025-07-31 | Started | Product: MYOB Implementation Owner: Jayshil Action Items: Setup company file and later opening balance – WIP Details sent to customer to verify. (Awaiting response) Issues: CUSTOMER DELAY Progress: 20% Total Billing: $3,905 Total Billed: $3,905 |  | 1
4 | Pay Global | Pay Global | PayGlobal | PayGlobal Ltd | 2025-07-09 | 2025-07-31 | Started | Product: Pay Global (On Prem) Owner: Jayshil Action Items: Create inhouse server – Completed. Download Fiji Setup files – Completed. Install configuration file. Check with vendor. Progress: 20% |  | 1
3 | LTA Project | LTA | Epicor | Senthil | 2022-07-01 | 2025-07-31 | In Progress | Epicor Upgrade From E7 to Kinetic | uploaded_files/MOM LTA-(24062025).docx | 1